## Group
Group 24: Gantt Chart (Group Schedule) | Fall 2022 | [16 empty] | Winter 2023 |  |  |  |  | Spring 2023
Members: Blake Huynh, Sean Mei, Ross Nikolai Montepalco, Ryan Nguyen | August |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
Tasks | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
Part 1: CMPE 195E (Fall 2022)
Project Selection
Project Abtract
Project Milestone Check
Mid-Semester Update
Workbook Part 1: Literature Search & Project Reqs
Project Report - Abstract, Ch.1 & 2
Final Project Presentation
Workbook Part 2: Design & Schedule
Project Report Ch. 3 - System Design
Project Report Final Submission After Sign Off
Schedule: Final Update
Individual Contribution Recommended by project Advisor
Part 2: Winter Break (Winter 2023)
Set up Linux Database Server via AWS
Order hardware and understand hardware specs/doc
Research and Understand PassKit (Apple Pay and Wallet)
Explore Raspberry Pi & understand how to read NFC and format data
Part 3: CMPE 195F (Spring 2023)
First Version of Front End Implementation
First Version of Database Component
First Version of Hardware Implementation
Milestone 1: First Version Testing
Final Version of Front End Implementation
Final Version of Database Component
Final Version of Hardware Implementation
Milestone 2: Final Version Testing
Expo Preparation

## Inidivdual
Group 24: Gantt Chart (Individual Tasks) | Spring 2023
Members: Blake Huynh, Sean Mei, Ross Nikolai Montepalco, Ryan Nguyen | January |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
Tasks | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
Individual Tasks
Purchase Items and Connection Testing
Prototype Hardware Connections using Breadboard
Raspberry Pi NFC Software Programming
Develop a Digital Card Directory (Database)
Develop a Digital Card Service
Develop Web Interface for Administrators
API Programming for Apple Digital Wallet
Software Testing using Custom-Made Test Cases
Raspberry Pi NFC Software Testing
Finalize Digital Card Directory (Database)
Finalize a Digital Card Service
Finalize Web Interface for Administrators
Implementing Printed Circuit Boards to Raspberry Pi
Finalize System Build Testing
Prepare Hardware Demo
Prepare Software Demo
Legend
Hardware Team
Software Team
Both Teams